## Outstanding Capex
06 Outstanding capital expenditure: Qamar Bay
Halcyon handover folder, 1 October 2031. Estimates in AED, excluding VAT.
Synthetic: for training only. Deep Hospitality.
Ref | Item | Category | Estimate (AED) | Status | Notes
CX-01 | Chiller 2 replacement (air-cooled chiller, 450 TR) | Building systems | 2400000 | Not started | Compressor running degraded since May 2031 with recurring high head pressure alarms; efficiency estimated 30% below rated. Replacement recommended before summer 2032. Not in the approved FY 2031/32 capex plan as Halcyon did not submit it.
CX-02 | Kitchen hood fire suppression upgrade | Life safety | 180000 | Quoted | Linked to snag SN-006.
CX-03 | Guestroom balcony door seals (all sea-facing rooms) | Building fabric | 320000 | Quoted | Recurring sand and noise complaints.
CX-04 | Spa extension: fire and life-safety drawing update and civil defence submission | Life safety | 85000 | Not started | See file 02.
CX-05 | Kids' club soft play refurbishment | FF&E | 140000 | Not started | Linked to snag SN-020.
CX-06 | Beach pavilion shade fabrics | FF&E | 95000 | Not started
CX-07 | Replacement PMS and booking engine (owner licences) | Information technology | 650000 | Not started | Required because Halcyon licences end at handover. See file 07.
|  | Total | 3870000